## readiness and impacts
Readiness and impacts
Authentia. Version 1.0. Reviewed 2026-10-29.
Blank template. Complete the amber cells with your team.
Review area | Question | Current evidence | Proposed role or workflow change | Readiness status | Preparation action | Owner | Open question or dependency | Review date
Purpose | Which business problem and next decision does the change address?
Roles | What will each role do differently and which decisions remain human?
Information and access | Which inputs and tools are approved for this use?
Capacity | When can people practise without compromising existing work?
Learning | Which task and checking routine must each role demonstrate?
Support | Who handles questions exceptions and the fallback?
Measurement | Which baseline definition population and period will support review?
Next decision | Who can approve a bounded first use and under which conditions?
Fictional worked example. Illustration only; replace with your own evidence.
Review area | Question | Current evidence | Proposed role or workflow change | Readiness status | Preparation action | Owner | Open question or dependency | Review date
Purpose | Which business problem and next decision does the change address? | Fictional planning scenario: internal request summaries; no benefits measured | Coordinators review a proposed summary before confirming routing | Needs preparation | Confirm problem and a bounded first group | Fictional workflow owner | Extent of avoidable review effort unknown | Before first-use decision
Roles | What will each role do differently and which decisions remain human? | Fictional current-process walkthrough note F1 | Sixteen coordinators would check completeness; two supervisors handle ambiguity | Needs preparation | Draft checking routine with role representatives | Fictional team manager | Downstream team must validate proposed handoff | Before first-use decision
Information and access | Which inputs and tools are approved for this use? | Fictional scenario permits synthetic practice inputs only | No live requests in practice; assistant takes no routing action | Needs preparation | Confirm access and approved practice environment | Fictional systems owner | Live information permissions not assessed | Before practice
Capacity | When can people practise without compromising existing work? | Fictional rota discussion F2; no allocation agreed | Proposed first group: four coordinators with cover | Unknown | Ask sponsor to resolve practice capacity | Fictional sponsor | Service cover and timing not agreed | Before practice
Learning | Which task and checking routine must each role demonstrate? | Fictional proposal F3; not yet tested | Review output; identify missing input; use manual fallback | Needs preparation | Prepare approved routine and exception cases | Fictional learning lead | Reviewer and feedback route to confirm | Before practice
Support | Who handles questions exceptions and the fallback? | Fictional operating note F4; escalation route incomplete | Supervisor handles ambiguity; coordinator can continue manually | Needs preparation | Agree support owner and cover | Fictional operations manager | Out-of-hours support not decided | Before first-use decision
Measurement | Which baseline definition population and period will support review? | Fictional baseline not collected | Compare completed checked work and total review effort | Unknown | Define eligible cases and collect baseline | Fictional workflow owner | Case mix and collection period to agree | Before value comparison
Next decision | Who can approve a bounded first use and under which conditions? | Fictional decision brief F5 is a proposal only | Sponsor reviews practice and support evidence | Needs preparation | Prepare decision record with unresolved conditions | Fictional sponsor | No rollout approval given | After preparation review

## stakeholder actions
Stakeholder actions
Authentia. Version 1.0. Reviewed 2026-10-29.
Blank template. Complete the amber cells with your team.
Affected group | Task or decision that changes | Learning or support need | Concern to investigate | Proposed engagement action | Evidence reference | Action owner | Dependency or open question | Status | Review point
Users
Team managers
Sponsor
Support and systems
Downstream recipients
Fictional worked example. Illustration only; replace with your own evidence.
Affected group | Task or decision that changes | Learning or support need | Concern to investigate | Proposed engagement action | Evidence reference | Action owner | Dependency or open question | Status | Review point
Fictional coordinators | Review assistant summary and confirm routing; no automatic assignment | Checking routine and manual fallback | Additional checking effort may offset drafting benefit | Walk through synthetic routine and incomplete requests | Fictional walkthrough F1 | Fictional team manager | Practice time not allocated | Proposed | Before first-use decision
Fictional supervisors | Resolve ambiguous or unsuitable cases | Escalation examples and support cover | Unclear destination for unusual requests | Review exception route with operational owner | Fictional operating note F4 | Fictional operations manager | Out-of-hours cover not agreed | Open | Before first-use decision
Fictional sponsor | Decide scope and preparation capacity | Evidence brief with unresolved assumptions | Initial group may lack cover | Decide whether to allocate time or reduce scope | Fictional rota discussion F2 | Fictional sponsor | Business priority to confirm | Decision needed | Before practice
Fictional systems owner | Maintain approved access for practice | Defined environment and synthetic data boundary | Live requests might be copied into practice | Confirm access and instructions with information owner | Fictional proposal F3 | Fictional systems owner | Live-use permissions outside current review | Open | Before practice
Fictional receiving team | Receive coordinator-confirmed record | Sample of proposed handoff | Summary may omit information needed downstream | Review proposed output against task requirements | Fictional handoff draft F6 | Fictional workflow owner | Output requirements need validation | Proposed | Before practice